## Sheet1
CBA Term Project
| 2023 (Year 0) | 2024 (Year 1) | 2025 (Year 2) | 2026 (Year 3) | 2027 (Year 4) | Total
Revenue | 0 | 1000 | 3000 | 5000 | 7000 | 16000
Gross Profit Margin |  | 40% | 40% | 45% | 45%
Gross Profit | 0 | 400 | 1200 | 2250 | 3150 | 7000
Benefits
Gross Profit | 0 | 400 | 1200 | 2250 | 3150 | 7000
Lower Training Costs | 0 | 50 | 100 | 150 | 200 | 500
Lower IT Costs | 0 | 20 | 20 | 20 | 20 | 80
Enhanced Reputation | 0 | 40 | 40 | 40 | 40 | 160
Total Benefits | 0 | 510 | 1360 | 2460 | 3410 | 7740
Costs
Software Hosting | 12 | 144 | 144 | 144 | 144 | 588
Software Development |  | 0 | 0 | 0 | 0 | 0
Database Hosting | 684 | 684 | 684 | 684 | 684 | 3420
Domain Name Ownership | 6 | 6 | 6 | 6 | 6 | 30
Operational Disruptions | 250 | 150 | 100 | 50 | 25 | 575
Total Costs | 952 | 984 | 934 | 884 | 859 | 4613
Cash Flow | -952 | -474 | 426 | 1576 | 2551
Cumulative Cash Flow | -952 | -1426 | -1000 | 576 | 3127
Interest Rate | Net Present Value | Internal Rate of Return
10% | 1895.5965 | 45.66%
35% | 339.2116 | 45.66%
Coefficient | 3.3333
Criteria | Weight | Score (0-3) | Weighted Score | 3 | 2 | 1 | 0 | Explanation
Technology Risk | 1.5 | ---- | 10.3333 | High | Medium | Low | None
Level of Complexity | 0.5 | 1 | 1.6667 | High | Medium | Low | None | The team is unable to implement the necessary technologies to construct the requried front end and back-end.
Level of Customization | 0.2 | 1 | 0.66667 | High | Medium | Low | None | The team is unable to provide the correct tools to upload profiles and CTF challenges
Configuration Detail | 0.8 | 3 | 8 | High | Medium | Low | None | Configuration of the site is misaligned and not working in its parameters
Security Risk | 3.6 | ---- | 36 | High | Medium | Low | None
Data Specificity | 1.6 | 3 | 16 | High | Medium | Low | None | Categories in the website is not broad/specifc enough to encompass all CTF challenges.
Cybersecurity threats | 2 | 3 | 20 | High | Medium | Low | None | Product has cybersecurity exploits that can steal CTF data or login data.
Organizational Complexity | 3.7 | --- | 19 | High | Medium | Low | None
Regulatory compliance | 1.2 | 2 | 8 | Many | Medium amount | Low | None units | Website does not follow regulatory compliance from RPI
Lack of User Acceptance | 0.8 | 2 | 5.3333 | High | Medium | Low | None | RCC does not accept using the product.
Change in Requirements | 1.2 | 1 | 4 | Most/All | Some | Few | None | Client changes the requirements of the website
Timeline | 0.5 | 1 | 1.6667 | Schedule very Busy | Schedule Midly Busy | Schedule Free | None | Team members are unable to have time to complete the project.
Implementation Risk | 1.2 | ---- | 8 | High | Medium | Low | None
Integration faults | 1.2 | 2 | 8 | High | Medium | Low | None | RPI login system is compatible with our site/Dotcio does not allow our site.
Risk Index (0-100) | Sum = 10 |  | 73.3333
|  |  | The following chart can be used to calculate Discount Rate | [5 empty] | Risk Category | Risk | Probability of Problem | Impact | Weight of Risk (% of all impacts) | Probability * Impact $$ | Probability*Impact Score Assuming 0-3 Range Rounded to Whole Number
[9 empty] | Technology | Level of Complexity | 30% | 100 | 5% | 30 | 1
|  |  | Risk Index | Discount Rate |  |  |  |  | Technology | Level of Customization | 20% | 50 | 3% | 10 | 1
|  |  | 90 - 100 | 50% |  |  |  |  | Technology | Configuration Detail | 40% | 200 | 8% | 80 | 3
|  |  | 80 - 89 | 40% |  |  |  |  | Security | Data Specificity | 20% | 400 | 16% | 80 | 3
|  |  | 70 - 79 | 30% |  |  |  |  | Security | Cybersecurity threats | 20% | 500 | 20% | 100 | 3
|  |  | 60 - 69 | 20% |  |  |  |  | Organizational Complexity | Regulatory compliance | 20% | 300 | 12% | 60 | 2
|  |  | 50 - 59 | 16% |  |  |  |  | Organizational Complexity | Lack of User Acceptance | 20% | 200 | 8% | 40 | 2
|  |  | 40 - 49 | 14% |  |  |  |  | Organizational Complexity | Change in Requirements | 10% | 300 | 12% | 30 | 1
|  |  | 30 - 39 | 12% |  |  |  |  | Organizational Complexity | Timeline | 10% | 100 | 4% | 10 | 1
|  |  | 20 - 29 | 8% |  |  |  |  | Implementation | Integration Faults | 20% | 300 | 12% | 60 | 2
|  |  | 10 - 19 | 6%
|  |  | 0 - 9 | 4% |  |  |  |  | Sum |  |  | 2450 | 100%
Note on A4: Manicke, Ben: These are just projected numbers. Our site is meant to have great outreach to our sponsors and donors, and we hope to have that contributes to our revenue increase. We eventually expect to see this number taper off but initially we could see a rapid increase in value.
Note on A9: Manicke, Ben: This is to reflect our impacts on labor costs. We predict training new developers on the site should become easier with time and the value should decrease.
Note on A10: Manicke, Ben: This is our impacts on material and contract costs. Following trends, we expect IT costs to drop in some regards and try to account for such drops here in our CBA.
Note on A11: Manicke, Ben: This is an intangible benefit. We believe as time progresses the site will be better known, and we could have potential help from some donors here and there.
Note on A14: Manicke, Ben: We were looking for places to host our site and found somewhere that will host our site for 1$ a month for one year while the following years will be 12$ a month. (Variable cost)
Note on A15: Manicke, Ben: We predict that our site will take 100$ to initially develop our site. (One time capital costs)
Note on A16: Manicke, Ben: To support the high amount of data it will be receiving from all the CTF writeups it will cost $684 a year to support that pricing plan on MongoDB. (Variable costs)
Note on A17: Manicke, Ben: Through a site we found it costs 6 dollars a year to purchase a .com for our site. (Fixed Costs)
Note on A18: Manicke, Ben: There obviously will be some mishaps when developing and setting up our site. We plan to account for this error but see it costing less as time passes (Intangible costs)