## Risk
Instructions: Enter the weight and score for each type of risk, and the explanation for it. (only the values in blue should be entered)
Coefficient | 3.3333
Criteria | Weight | Score (0-3) | Weighted Score | 3 | 2 | 1 | 0 | Explanation
Technology Risk | 0 | ---- | 10.3333 | High | Medium | Low | None
Level of Complexity | 0.5 | 1 | 1.6667 | High | Medium | Low | None | The team is unable to implement the necessary technologies to construct the requried front end and back-end.
Level of Customization required | 0.2 | 1 | 0.66667 | High | Medium | Low | None | The team is unable to provide the correct parameters/parameters are unable to be enforced
Configuration Detail required | 0.8 | 3 | 8 | High | Medium | Low | None
Security Risk | 0 | ---- | 36 | High | Medium | Low | None
Data Specificity | 1.6 | 3 | 16 | High | Medium | Low | None | Categories in the website is not broad/specifc enough to encompass all CTF challenges.
Cybersecurity threats | 2 | 3 | 20 | High | Medium | Low | None | Product has cybersecurity exploits that can steal CTF data or login data.
Organizational Complexity | 0 | --- | 17.3333 | High | Medium | Low | None
Regulatory compliance | 1.2 | 2 | 8 | Many | Medium amount | Low | None units | Website does not follow regulatory compliance from RPI
Lack of User Acceptance | 0.8 | 2 | 5.3333 | High | Medium | Low | None | RCC does not accept using the product.
Change in Requirements | 1.2 | 1 | 4 | Most/All | Some | Few | None | Client changes the requirements of the website
Implementation Risk | 0 | ---- | 9.6667 | High | Medium | Low | None
Timeline | 0.5 | 1 | 1.6667 | Schedule very Busy | Schedule Midly Busy | Schedule Free | None | Team members are unable to have time to complete the project.
Integration faults | 1.2 | 2 | 8 | High | Medium | Low | None | RPI login system is compatible with our site/Dotcio does not allow our site.
Risk Index (0-100) | Sum = 10 |  | 73.3333
10 |  |  | The following chart can be used to calculate Discount Rate
|  |  | Risk Index | Discount Rate
|  |  | 90 - 100 | 50%
|  |  | 80 - 89 | 40%
|  |  | 70 - 79 | 30%
|  |  | 60 - 69 | 20%
|  |  | 50 - 59 | 16%
|  |  | 40 - 49 | 14%
|  |  | 30 - 39 | 12%
|  |  | 20 - 29 | 8%
|  |  | 10 - 19 | 6%
|  |  | 0 - 9 | 4%