## Sheet1
Rick Management In-Class Exercise 1. Download the "Risk Analysis Excel Spreadsheet" from LMS 2. Using the "Risk Category", "Risk", "Probability of Problem", and "Impact" data below, complete "Weight of Risk", "Probability*Impact $$", and "Probability*Impact Score" Columns 3. Use the "Weight of Risk" values and the "Probability*Impact Score" data to populate the "Weight" and "Score" values for each type of Risk in the "Risk Analysis Spreadsheet" 4. Find the "Risk Index" and the associated "Discount Rate" for this scenario 5. Insert the "Discount Rate" from this scenario into your CBA In-Class Exercise Spreadsheet and determine the NPV for the Project 6. Insert the answer to question 5 into this spreadsheet in cell A16 with red font color. 7. Submit this "Risk Managment In-Class Exercise" Spreadsheet with a file name that begins with your last name and the Edited "Risk Analysis" Spreadsheet with a file name that begins with your last name on LMS.
Risk Category | Risk | Probability of Problem | Impact | Weight of Risk (% of all impacts) | Probability * Impact $$ | Probability*Impact Score Assuming 0-3 Range Rounded to Whole Number
Technology | Level of Complexity | 30% | 100 | 5% | 30 | 1 | 0.06
Technology | Level of Customization | 20% | 50 | 2.04% | 10 | 1 | 0.02
Technology | Configuration Detail | 40% | 200 | 8% | 80 | 3 | 0.16
Security | Data Specificity | 20% | 400 | 16% | 80 | 3 | 0.16
Security | Cybersecurity threats | 20% | 500 | 20% | 100 | 3 | 0.2
Organizational Complexity | Regulatory compliance | 20% | 300 | 12% | 60 | 2 | 0.12
Organizational Complexity | Lack of User Acceptance | 20% | 200 | 8% | 40 | 2 | 0.08
Organizational Complexity | Change in Requirements | 10% | 300 | 12% | 30 | 1 | 0.06
Implementation | Timeline | 10% | 100 | 5% | 10 | 1 | 0.02
Implementation | Integration Faults | 20% | 300 | 12% | 60 | 2 | 0.12
Sum |  |  | 2450 | 100% | 500 | 19
-18205
Technical Challenges
Cybersecurity threats
Lack of User Adoption
Data Security
Change in Requirements
Integration faults
Data Integrity
Scope Creep
Regulatory compliance
Client/Organization Approval
Third Party Approval